## Sheet1
Task | Estimated (Hours) - Anik | Estimation (Hours)-Ishtiak | Estimation (Hours)-Riaz | Estimation (Hours)-Shahnawaz
Login Screen | 8 | 0 | 0 | 0
Layout Design | 1
Login with facebook | 2
Login with google | 3
Screen functionality | 1
Localization support | 1
Start Screen | 6 | 0 | 0 | 0
Layout design | 2
Save user data in backend | 2
Screen functionality | 1
Localization support | 1
Home Screen | 17 | 0 | 0 | 0
Layout design | 4
Fetch data from server/parse | 2
Save fetched data in local database of parse | 2
Side Navigation implementation | 6
Show data in table view | 1
Screen functionality | 1
Localization support | 1
Give Screen | 16 | 0 | 0 | 0
Layout design | 3
Pick image from image picker | 2
Populate the category drop down/action sheet | 2
Pick up place | 4
Send data in backend/parse | 2
Screen functionlity | 2
Localization support | 1
Me Screen | 9 | 0 | 0 | 0
Layout design | 2
Fetch user data from Parse | 2
Fetch remarks list from Parse | 1
Edit option layout design | 2
Update edited data in parse | 2
Give & Need Screen / Category Screen | 8 | 0 | 0 | 0
Layout design | 4
Populate Collection view using give and need category list | 2
Screen functionality | 1
Localization support | 1
Map Screen | 13 | 0 | 0 | 0
Layout design | 1
Integrate map | 4
Fetch data of Give from Parse | 2
Populate map using fetched data | 3
Screen functionality | 2
Localization support | 1
Give Detail Screen | 9 | 0 | 0 | 0
Layout design | 2
Implement chat option(Quickblox) | 4
Screen functionality | 2
Localization support | 1
Search Screen | 4 | 0 | 0 | 0
Fetch data from parse using user query | 2
Show fetched list in Home Screen/ Map Screen | 2
Ranklist Screen | 7 | 0 | 0 | 0
Layout design | 3
Fetch data of rank from parse | 2
Screen functionality | 1
Localization support | 1
Subscribe Option and Buy Coffe option imaplementation | 4
Image and Other UI component change | 8
Animation and other UX | 8
Total Time Estimated(Hours) | 117 | 0 | 0 | 0
Total Time Estimated(Days/Person) | 39 | 0 | 0 | 0
Total Software Engineer | 3 | 3 | 3 | 3
Should be completed within (days) | 13 | 0 | 0 | 0